## matrix-1
MATRIX 1
The 2010-2016 MTPDP: Priority Strategies and Activities
Table 1. Strategy Planning Matrix
Outcome | Priority Strategy | Priority Activities | Responsible Agency/ies | Measurable Output Targets
|  |  |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | TOTAL
Ensure energy security | Attain nationwide electrification | Pursue Sitio Electrification Program from 69% level in 2009 to 91% in 2016 | NEA | 644 | 1500 | 4172 | 4253 | 4459 | 4403 | 3318 | 22749
|  | Pursue Barangay Line Enhancement Program for 2,195 barangays | NEA |  | 300 | 379 | 379 | 379 | 379 | 379 | 2195
|  | Sustain connection of consumers from 74% in 2009 to 90% in 2016 | NEA | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 2100000

## matrix-2
MATRIX 2
The 2010-2016 Medium-Term Public Investment Program
Table 2. Agemcy Three-Year Rolling Public Investement List (PIL)
Priority Strategies and Activities (PSAs) | MFO | Programs and Projects (PAPs) | Spatial Coverage | 2010 |  |  | 2011 |  |  | 2012 |  |  | Later Years
|  |  |  | Target | OVI | Cost Estimate (Php M) | Target | OVI | Cost Estimate (Php M) | Target | OVI | Cost Estimate (Php M)
Attain nationwide electrification | Rural Electrification | Sitio Electrification Program | Nationwide | 644 | Number of Sitios energized | 644 | 1500 | Number of Sitios energized | 1500 | 4172 | Number of Sitios energized | 4172
|  | Barangay Line Enhancement Program | Nationwide |  |  |  | 300 | Number of barangay lines enhanced | 450 | 379 | Number of Sitios energized | 569
TOTAL |  |  | 7335 |  |  | 644 |  |  | 1950 |  |  | 4741
Notes:
MFO |  | - | Major Final Output
OVI |  | - | Objective and Verifiable Indicators
Spatial Coverage |  | - | indicate whether the PAP is located nationwide or inter-regional specific. If region specific, indicate the region and province/s

## Sheet3
Annex B
MEDIUM-TERM PHILIPPINE DEVELOPMENT PLAN (2010-2016)
NATIONAL ELECTRIFICATION ADMINISTRATION
Pillar I: | Ensure Energy Security
OUTCOME | STRATEGIES | ACTIVITIES | AGENCY | MEASURABLE OUTPUTS/TARGETS
|  |  |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | TOTAL
Ensure Energy Security | Attain nationwide electrification | Pursue Sitio Electrification Program from 69% level in 2009 to 91% in 2016 | NEA | 644 | 1500 | 4172 | 4253 | 4459 | 4403 | 3318 | 22749
|  | Pursue Barangay Line Enhancement Program for 2,195 barangays | NEA |  | 300 | 379 | 379 | 379 | 379 | 379 | 2195
|  | Sustain connection of consumers from 74% in 2009 to 88% in 2016 | NEA | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 2100000