## Canvass Sheet
DINAGAT ISLAND ELECTRIC COOPERATIVE, INC.
Justiniana, San Jose, Province of Dinagat Islands
CANVASS SHEET
________________________ |  |  |  | Date: | Oct. 5, 2015
________________________
Greetings!
Please indicate the charges for the installation of housewiring materials which this Cooperative, desires to request
from you as indicated hereunder to wit:
Item # | Description | Qty. | Unit | Unit Cost | Amount
1 | Housewiring installation per household | 370 | HH
SEP 2015 Additional (19 sitios)
***nothing follows***
Canvassed by: |  |  | Enterprises/Company:
________________________ |  |  | _________________________
DINAGAT ISLAND ELECTRIC COOPERATIVE, INC.
Justiniana, San Jose, Province of Dinagat Islands
CANVASS SHEET
________________________ |  |  |  | Date: | Oct. 5, 2015
________________________
Greetings!
Please indicate the charges for the installation of housewiring materials which this Cooperative, desires to request
from you as indicated hereunder to wit:
Item # | Description | Qty. | Unit | Unit Cost | Amount
1 | Housewiring installation per household | 370 | HH
SEP 2015 Additional (19 sitios)
***nothing follows***
Canvassed by: |  |  | Enterprises/Company:
________________________ |  |  | _________________________

## Abstract of Canvass
DINAGAT ISLAND ELECTRIC COOPERATIVE, INC.
Justiniana, San Jose, Dinagat Islands
ABSTRACT OF CANVASS
Item # | DESCRIPTION | Qty. | Unit | SUPPLIER |  |  | Winning Contractor
|  |  |  | PENASBO, JULIUS | LOPEZ, JUMARI | BRIONES, JOESEL | PENASBO, JULIUS
|  |  |  | Unit Cost | Unit Cost | Unit Cost
1 | Housewiring installation per household | 370 | HH | 485 | 490 | 500 | 179450
SEP 2015 Additional (19 sitios)
TOTAL: | [6 empty] | 179450
Prepared by: |  | Checked by: |  |  |  | Noted by:
SHERYL D. LITANG |  | MARY JOY U. LUENGO |  |  |  | SERGIO C. DAGOOC
FSD Staff W.O.O./Acting Internal Auditor General Manager
DINAGAT ISLAND ELECTRIC COOPERATIVE, INC.
Justiniana, San Jose, Dinagat Islands
SUMMARY OF CANVASS
Item # | DESCRIPTION | Qty. | Unit | SUPPLIER |  |  | Winning Contractor
|  |  |  | PENASBO, JULIUS | LOPEZ, JUMARI | BRIONES, JOESEL | PENASBO, JULIUS
|  |  |  | Unit Cost | Unit Cost | Unit Cost
1 | Housewiring installation per household | 370 | HH | 485 | 490 | 500 | 179450
SEP 2015 Additional (19 sitios)
TOTAL: | [6 empty] | 179450
Prepared by: |  | Checked by: |  |  |  | Noted by:
SHERYL D. LITANG |  | MARY JOY U. LUENGO |  |  |  | SERGIO C. DAGOOC
FSD Staff W.O.O./Acting Internal Auditor General Manager

## Procurement Activity (2)
RECOMMENDED EARLIEST POSSIBLE TIME AND MAXIMUM PERIOD ALLOWED FOR THE PROCUREMENT OF INFRASTRUCTURE PROJECTS FOR (13) SITIOS/PUROKS FUNDED BY 2020 SEP SUBSIDY
Section | Procurement Activity | Minimum Calendar Days Recommended for Activity | Operational Timeline(Recommended Earliest Possible Time) | Conditions/Remarks
20 | Pre-Procurement Conference | 1 | Day 0 | Optional for ABC of Php 5,000.000.00 and below
21.2.1 | Advertisement/Posting of Invitation to Bid | 7 CDs Aug. 26, 2020 to Sept. 1, 2020 | Days 1 to 7 | Start of Availability of Bidding Documents
22.2 | Pre-bid Conference | 1 CD September 2, 2020 | Day 8 | *Optional for ABC below Php 1,000.000.00 * Not earlier than 7 CDs from Advertisement/Posting * 12 CDs before Deadline of Submission and Receipt of Bids
25.5 | Deadline of Submission and Receipt of Bids/Bid Opening | 1 CD September 14, 2020 9:00a.m. | Day 20 | Last Day of Availability of Bidding Documents
32.4 | Bid Evaluation | 1 CD September 15, 2020 | Day 21
34.8 | Post- Qualification | 2 CDs September 16-17, 2020 | Day 22 to 23 | The Bidder must submit all Post-Qualification requirements within 5 CDs from receipt of notice as bidder with LBC in accordance with Sec. 34.2
37.1.2 | Approval of Resolution/Issuance of Notice of Award | 1 CD September 18, 2020 | Day 24
37.2.1 | Contract Preparation and Signing | 1 CD September 19, 2020 | Day 25
37.3 | Approval of Contract by higher authority | 1 CD |  | if necessary
37.4.1 | Issuance of Notice to Proceed | 1 CD September 20,2020 | Day 26
TOTAL TIME |  |  | 26 CDs | Excluding Approval of Higher Authority, if applicable
Submitted by:
(SGD.)PETERLA Z. TRANGIA
BAC Chairperson
Note on C8: Admin:

## Calendar
Bidding activities for SEP 2020 (13) sitios
2020-07-01 | [6 empty] | 2020-08-01
SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT
|  |  | 1 | 2 | 3 | 4 | [6 empty] | 1
5 | 6 | 7 | 8 | 9 | 10 | 11 | 2 | 3 | 4 | 5 | 6 | 7 | 8
12 | 13 | 14 | 15 | 16 | 17 | 18 | 9 | 10 | 11 | 12 | 13 | 14 | 15
19 | 20 | 21 | 22 | 23 | 24 | 25 | 16 | 17 | 18 | 19 | 20 | 21 | 22
26 | 27 | 28 | 29 | 30 | 31 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29
[7 empty] | 30 | 31
2020-09-01 | [6 empty] | 2020-10-01
SUN | MON | TUES | WED | THURS | FRI | SAT | SUN | MON | TUES | WED | THURS | FRI | SAT
|  | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3
6 | 7 | 8 | 9 | 10 | 11 | 12 | 4 | 5 | 6 | 7 | 8 | 9 | 10
13 | 14 | 15 | 16 | 17 | 18 | 19 | 11 | 12 | 13 | 14 | 15 | 16 | 17
20 | 21 | 22 | 23 | 24 | 25 | 26 | 18 | 19 | 20 | 21 | 22 | 23 | 24
27 | 28 | 29 | 30 |  |  |  | 26 | 26 | 27 | 28 | 29 | 30 | 31
NOTE:
Pre-Bid - September 2, 2020
Bid Opening - September 14, 2020 @ 9:00 a.m.